## Start Here
13-Week Construction Cash Flow Forecast
Your payday weather report, built by Out of the Box Advisors
How to use it
1 | Setup: Enter the cash in your bank today, your cash floor (the lowest balance you're comfortable with), and your regular company bills with the day each one is due.
2 | Jobs: List each active job with its contract value and budget, then enter the cash you expect in and out each week.
3 | Forecast: Check your weekly weather. Clear means you're above your floor, cloudy means you've dipped below it, and storm means you're projected to run out.
4 | Job Check: Compare your honest estimate to finish each job with the cash that's actually there for it. That's how you spot robbing Peter to pay Paul.
Legend
1000 | Light purple cells with purple numbers are yours to edit. Type right over the example values.
1000 | White cells calculate for you. They're locked so a stray keystroke can't break the math.
The example jobs are already filled in so you can see how everything connects. Replace them with your own, or clear them out and start fresh. Seeing blank numbers? Click Enable Editing at the top of Excel and everything will calculate.
Want help reading your forecast? Book a free business coaching consultation with Out of the Box Advisors.
Read the guide: Construction Cash Flow: Why Trades Businesses Run Out of Money (and How to Stop It)
This template is a planning tool, not financial, tax, or legal advice. Review your numbers with your CPA.
Template version 1.0, October 2026.

## Setup
Setup
Your starting point and the bills you pay no matter what jobs are running
Your business
Business name | Your Company Name
Forecast start date (a Monday) | 2026-11-02 |  | Week 1 starts here.
Cash in the bank today | 28000 |  | Your actual balance, not what's owed to you.
Your cash floor | 15000 |  | The lowest balance you're comfortable with.
Regular company bills
Bill | Amount | How often | Due day | Avg per week
Office and admin payroll | 900 | Weekly |  | 900
Shop or office rent | 2200 | Monthly | 1 | 507.6923
Insurance | 1500 | Monthly | 15 | 346.1538
Vehicles and fuel | 500 | Weekly |  | 500
Software and phones | 450 | Monthly | 5 | 103.8462
Equipment and loan payments | 1600 | Monthly | 20 | 369.2308
Tax set-aside | 400 | Weekly |  | 400
Owner pay | 800 | Weekly |  | 800
0
0
Average company bills per week |  |  |  | 3926.9231
Weekly bills hit every week. Monthly bills land in the week they're actually due, so your forecast shows the real tight weeks instead of averaging them away. Forgot a due day? It's treated as the 1st until you add one. Quarterly or yearly bills go on the Jobs tab as one-time payments.

## Jobs
Jobs
Every active job, plus the cash you expect in and out each week. One job, one budget, one plan.
Job | Type | Contract | Job budget (materials, labor, subs) | Gross profit (before overhead) | Gross margin |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | 13-week total
[7 empty] | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
Smith roof replacement | Roofing | 28000 | 21000 | 7000 | 25% | Cash in | 2026-11-16: 14000; 2026-11-30: 11200 | 25200
[6 empty] | Cash out | 2026-11-09: 6000; 2026-11-16: 4500; 2026-11-30: 2000 | 12500
Garcia kitchen remodel | Remodel | 64000 | 49500 | 14500 | 22.66% | Cash in | 2026-12-07: 19200; 2026-12-28: 19200; 2027-01-18: 19200 | 57600
[6 empty] | Cash out |  |  |  | 6000 | 6000 | 5000 | 5000 | 4000 | 3500 | 3000 | 4000 | 1000 |  | 37500
Patel HVAC system install | HVAC | 14500 | 10900 | 3600 | 24.83% | Cash in | 2026-11-30: 13050 | 13050
[6 empty] | Cash out | 2026-11-30: 3100 | 3100
Lakeside home addition | Addition | 120000 | 96000 | 24000 | 20% | Cash in | 2026-12-07: 30000; 2026-12-28: 30000; 2027-01-25: 30000 | 90000
[6 empty] | Cash out |  |  | 7000 | 6000 | 6000 | 7000 | 6000 | 6000 | 7000 | 6000 | 6000 | 5000 | 8000 | 70000
Nguyen re-roof | Roofing | 32000 | 24000 | 8000 | 25% | Cash in | 2026-12-21: 3200; 2027-01-04: 16000; 2027-01-18: 12800 | 32000
[6 empty] | Cash out | 2026-12-21: 9000; 2026-12-28: 7000; 2027-01-04: 6000; 2027-01-18: 2000 | 24000
[6 empty] | Cash in | [13 empty] | 0
[6 empty] | Cash out | [13 empty] | 0
[6 empty] | Cash in | [13 empty] | 0
[6 empty] | Cash out | [13 empty] | 0
[6 empty] | Cash in | [13 empty] | 0
[6 empty] | Cash out | [13 empty] | 0
One-time company payments (quarterly taxes, big repairs, renewals) | [5 empty] | Cash out | 2026-12-07: 6000; 2027-01-04: 2500 | 8500
Other cash in (line of credit draws, owner money, refunds) | [5 empty] | Cash in | [13 empty] | 0
Total job cash in | [6 empty] | 0 | 0 | 14000 | 0 | 24250 | 49200 | 0 | 3200 | 49200 | 16000 | 0 | 32000 | 30000 | 217850
Total job cash out | [6 empty] | 0 | 6000 | 11500 | 12000 | 17100 | 12000 | 11000 | 19000 | 17500 | 15000 | 10000 | 8000 | 8000 | 147100
Enter what's still ahead from today: cash you'll collect and cash you'll spend in each week. Expecting retainage back? Put it in the week you realistically expect the check, not the week the job wraps. Running more than eight jobs? Group small service calls into one line.

## Forecast
Your Company Name ¦ 13-Week Cash Flow Forecast
Your payday weather report. Clear skies above your floor, clouds below it, storms when the money runs out.
| LOWEST PROJECTED CASH |  |  | WEEKS BELOW YOUR FLOOR |  |  | JOB CASH COMING IN |  |  | CASH AT WEEK 13
| -6050 |  |  | 7 |  |  | 217850 |  |  | 41400
| in the week of Dec 21 |  |  | Time to plan around them |  |  | over the next 13 weeks |  |  | above your floor
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Week starting | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
Opening cash | 28000 | 24950 | 14850 | 13150 | -1450 | 450 | 29050 | 12350 | -6050 | 20850 | 16300 | 2200 | 22000
Job cash in | 0 | 0 | 14000 | 0 | 24250 | 49200 | 0 | 3200 | 49200 | 16000 | 0 | 32000 | 30000
Other cash in | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job cash out | 0 | -6000 | -11500 | -12000 | -17100 | -12000 | -11000 | -19000 | -17500 | -15000 | -10000 | -8000 | -8000
Company bills | -3050 | -4100 | -4200 | -2600 | -5250 | -2600 | -5700 | -2600 | -4800 | -3050 | -4100 | -4200 | -2600
One-time payments | 0 | 0 | 0 | 0 | 0 | -6000 | 0 | 0 | 0 | -2500 | 0 | 0 | 0
Net change | -3050 | -10100 | -1700 | -14600 | 1900 | 28600 | -16700 | -18400 | 26900 | -4550 | -14100 | 19800 | 19400
Closing cash | 24950 | 14850 | 13150 | -1450 | 450 | 29050 | 12350 | -6050 | 20850 | 16300 | 2200 | 22000 | 41400
Your cash floor | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Cushion above floor | 9950 | -150 | -1850 | -16450 | -14550 | 14050 | -2650 | -21050 | 5850 | 1300 | -12800 | 7000 | 26400
Forecast | ☀ Clear | ☁ Cloudy | ☁ Cloudy | ⚡ Storm | ☁ Cloudy | ☀ Clear | ☁ Cloudy | ⚡ Storm | ☀ Clear | ☀ Clear | ☁ Cloudy | ☀ Clear | ☀ Clear

## Job Check
Job Check: Can Each Job Pay for Itself?
If a job can't finish without the next customer's deposit, you're robbing Peter to pay Paul. This is where you find out.
Job | Contract | Job budget | Spent so far | Budget left | Your honest estimate to finish | Cash set aside for this job | Payments due before it's finished (not the final payment) | Covered by | Gap | Status
Smith roof replacement | 28000 | 21000 | 8500 | 12500 | 12500 | 2000 | 14000 | 16000 | 0 | ✔ Pays for itself
Garcia kitchen remodel | 64000 | 49500 | 13500 | 36000 | 37500 | 3000 | 38400 | 41400 | 0 | ▲ Covered, but over budget
Patel HVAC system install | 14500 | 10900 | 7800 | 3100 | 3100 | 0 | 0 | 0 | 3100 | ⚠ Waiting on the next deposit
Lakeside home addition | 120000 | 96000 | 26000 | 70000 | 70000 | 6000 | 60000 | 66000 | 4000 | ⚠ Waiting on the next deposit
Nguyen re-roof | 32000 | 24000 | 0 | 24000 | 24000 | 0 | 19200 | 19200 | 4800 | ⚠ Waiting on the next deposit
Existing work currently waiting on future customers' deposits | [8 empty] | 11900
That's how much of your current work depends on deposits you haven't collected yet. Shrink this number first.
Budget left = job budget minus what you've spent. Your honest estimate to finish is what it will really take, which can be more than the budget left. Covered by = cash already set aside for the job plus payments due before it's finished. Don't count the final payment you get when the job is done; that's the point of the test. Anything short is the gap.